Executive Summary

Sustainable Food Plan, West Northamptonshire 2026–2030

Our Vision

Together, we will create a healthier, fairer and more sustainable food system across West Northamptonshire where everyone has access to affordable, nutritious and culturally appropriate food, communities are empowered to grow, cook and enjoy good food, local food businesses can thrive, and our food system supports environmental sustainability.

Why This Matters

Food has a significant impact on health, wellbeing, communities, the local economy and the environment. Improving our local food system can help to:

- Improve health and reduce obesity across all ages.

- Reduce food insecurity and food poverty.

- Support healthy ageing and child development.

- Strengthen local food businesses and employment.

- Increase skills in cooking and growing food.

- Reduce food waste and environmental impacts.

- Promote sustainable local food production and procurement.

| Strategic Outcome | What Success Looks Like by 2030 |
| --- | --- |
| Flourishing Food Culture | Residents, communities, statutory services and businesses understand, value and engage with good food, cooking and growing opportunities |
| Healthy & Affordable Food | More people can access nutritious food and support to maintain a healthy weight |
| Sustainable Local Food Economy | Strong local food businesses, workforce, procurement and supply chains |
| Smarter Catering and procurement | Shared procurement and catering standards with a focus on local food |
| Environmentally Sustainable Food System | Less food waste, more local growing and more sustainable food production |

Our Five Strategic Outcomes

1. A Flourishing Local Food Culture and Movement

We will strengthen the West Northamptonshire Sustainable Food Network and increase opportunities for residents to access information, support and activities relating to cooking, growing and healthy eating.

By 2030 we will:

- Have a strong and sustainable Food Network.

- Improve community knowledge and engagement with good food.

- Increase participation in cooking and growing activities.

- Strengthen food education across the lifecourse.

- Build a strong evidence base demonstrating impact.

2. Increased Access to Healthy, Affordable and Culturally Relevant Food

We will work together to ensure that people can access healthy food and appropriate support regardless of income, age or circumstance.

By 2030 we will:

- Improve healthy weight outcomes.

- Provide clear pathways to services and support.

- Strengthen Family Hub and Healthy Start delivery.

- Expand food larder and wraparound support provision.

- Reduce food insecurity and inequalities.

3. A Sustainable, Resilient and Inclusive Food Economy

We will support local food businesses, workforce development, sustainable procurement and local food production.

By 2030 we will:

- Strengthen links across the food economy.

- Increase opportunities for local businesses.

- Improve skills and employment pathways.

- Promote sustainable local sourcing and procurement.

- Support healthier food environments through policy and planning.

4. Encourage Smarter Catering and procurement

We will increase the procurement, promotion and consumption of healthy, sustainable and locally sourced food across public sector organisations, anchor institutions, businesses and community settings, supporting local suppliers and healthier food environments.

By 2030 we will:

- Strengthen and influence procurement partnerships

- Increase procurement of local food

- Encourage Anchor Institutions to showcase good procurement

- Develop a shared food policy

5. Environmentally Responsible and Sustainable Food Systems

We will reduce food waste, increase local growing opportunities and promote environmentally responsible food practices.

By 2030 we will:

- Reduce food waste across households and businesses.

- Increase redistribution of surplus food.

- Expand community growing opportunities.

- Support sustainable food production.

- Increase public engagement in sustainable food behaviours.

How We Will Deliver This Plan

The Food Plan will be delivered through partnership working across:

- West Northamptonshire Sustainable Food Network

- West Northamptonshire Council

- NHS and Public Health partners

- Community and voluntary organisations

- Educational settings

- Local businesses and producers

- Residents and community groups

Progress will be monitored through annual reporting and regular review by the West Northamptonshire Sustainable Food Network.

Strategic Outcome 1

Build a Flourishing Local Food Culture and Movement that Promotes Sustainable and Healthy Food

| Objective | Priority Actions | Success Measures |
| --- | --- | --- |
| Strengthen and grow the WNSFN | Maintain governance arrangements, secure funding, increase membership, improve representation of communities and organisations | Governance structure established; funding secured; membership increased by 200 by 2027 and 400 by 2029; increased pledges from residents and organisations |
| Develop food intelligence and community insight | Publish Food Profile; undertake Big Conversation engagement; identify data gaps; establish ongoing engagement mechanisms; utilise School Health Unit Survey findings | Food Profile published and regularly updated; evidence of community insight informing priorities; data gaps addressed |
| Improve awareness of local food opportunities | Deliver communications strategy; website and resource hub; newsletters; campaigns; food asset mapping | Increased public awareness; website established; food asset map available; increased access to services and opportunities |
| Increase cooking, growing and healthy eating skills | Develop Food MECC programme; train workforce; relaunch Grow Cook Eat; develop Food Champions; promote community projects | MECC programme implemented; increased workforce training; active Food Champions network; increased participation in projects |
| Support food education across the lifecourse | Embed food themes in Healthy Early Years; increase Healthy Schools participation; promote Food for Life Served Here; develop Healthy Ageing and Workplace opportunities | Increased school participation; healthy eating embedded across settings; greater engagement across the lifecourse |
| Build evidence and showcase good practice | Produce case studies; evaluate impact; share learning; showcase local innovation | Strong evidence base established; annual showcase of good practice; increased awareness of successful projects |

Strategic Outcome 2

Increase Access to Healthy, Safe, Affordable and Culturally Relevant Food

| Objective | Priority Actions | Success Measures |
| --- | --- | --- |
| Improve healthy weight services and pathways | Develop clear pathways; increase awareness of services; improve referral routes; monitor service performance | Published pathways; improved access and outcomes; equitable service delivery |
| Support families to eat well | Develop family-focused programmes; embed healthy eating within Family Hubs; implement Healthy Start; expand Food MECC training | Increased family engagement and take-up of support services |
| Reduce food insecurity | Expand Food Larders; strengthen wraparound support; implement Food Bank to Food Larder recommendations; improve monitoring | Increased Food Larder provision and improved support for residents experiencing hardship |
| Strengthen partnership approaches to poverty reduction | Align food support with anti-poverty initiatives and community support programmes | Improved system coordination and reduced food insecurity impacts |
| Maintain and strengthen high food safety standards | Strengthen collaboration with Environmental Health and partners; identify opportunities for shared priorities and reporting arrangements with the Food Plan | Continued compliance with food safety standards and improved partnership working |

Strategic Outcome 3

Build a Sustainable, Resilient and Inclusive Local Food Economy

| Objective | Priority Actions | Success Measures |
| --- | --- | --- |
| Strengthen local food networks and businesses | Map food infrastructure; align with Growth Hub, Food Tourism and Made in Northamptonshire; promote local food businesses and awards | Improved network connections; greater visibility of local food businesses; increased participation in food economy initiatives |
| Develop the future food workforce | Work with colleges, universities and employers; promote careers; support Great Service initiative; strengthen employment pathways | Increased workforce opportunities; greater engagement with training and employment pathways; improved sector skills base |
| Improve food policy and planning | Support implementation of planning policy; strengthen advertising restrictions; develop food policy approaches | Adoption and implementation of planning policies supporting healthy food environments |
| Improve procurement and local sourcing | Establish procurement working group; engage Anchor Institutions; increase local and sustainable procurement; share best practice | Increased procurement of local food; stronger procurement partnerships; greater promotion of Food for Life standards |
| Support sustainable food production and processing | Develop partnerships across production, processing and supply chains; identify opportunities for collaboration and innovation | Increased collaboration across the food system and stronger local food supply chain connections |

Strategic Outcome 4

Encourage Smarter Catering and Procurement

| Objective | Priority Actions | Success Measures |
| --- | --- | --- |
| Strengthen procurement partnerships | Increase membership of the WNSFN from procurement, catering, retail and hospitality sectors. Develop relationships with procurement leads across public, voluntary and business sectors. | Increased representation from procurement and catering sectors within the Network. |
| Understand and influence local food procurement | Map procurement opportunities and identify where local food can be incorporated into services, events and contracts. Develop a procurement working group to coordinate activity. | Procurement opportunities identified and action plan developed. |
| Increase procurement of local food | Work with public sector organisations, businesses and community organisations to increase purchasing of local, seasonal and sustainably produced food where possible. | Increased number of organisations actively procuring local food. |
| Support Anchor Institutions | Engage NHS organisations, West Northamptonshire Council and other anchor institutions to champion local food procurement and share learning across the system. | Anchor institutions actively involved in food procurement initiatives and sharing best practice. |
| Develop food policy and procurement standards | Explore the development of food policy and procurement approaches that promote healthy eating, sustainability and local sourcing. | Food policy principles agreed and embedded within organisational practice. |
| Promote sustainable and healthy catering | Support caterers to source sustainable food and integrate local supply chains into their operations. Promote healthier catering standards and best practice. | More catering providers demonstrating sustainable and healthy sourcing practices. |
| Increase uptake of recognised standards | Promote schemes such as Food for Life Served Here and showcase organisations that have achieved recognised food standards. | Increased awareness and uptake of recognised food standards. |
| Share and celebrate good practice | Identify and showcase organisations successfully implementing local procurement and sustainable catering approaches. | Annual examples of good practice shared through the Network. |

Strategic Outcome 5

Environmentally Responsible and Sustainable Food Systems

| Objective | Priority Actions | Success Measures |
| --- | --- | --- |
| Reduce food waste | Support implementation of the Waste Plan; promote reduce, reuse and recycle campaigns; develop composting initiatives | Reduction in household and commercial food waste |
| Increase redistribution of surplus food | Map surplus food provision; strengthen redistribution pathways; connect organisations and initiatives | Increased quantities of food redistributed locally |
| Increase opportunities for community food growing | Implement Gardening Policy; identify growing spaces; promote local growing initiatives | Increased number of growing sites and participants |
| Strengthen environmental partnerships | Work with climate, sustainability and farming partners; engage Parish and Town Councils | Stronger partnership activity and environmental action across the Network |
| Promote sustainable food production and innovation | Support NACRE developments; encourage sustainable food initiatives and innovation | Greater awareness and adoption of sustainable food practices |